## GANTT VIEW
|  |  | Actual Gantt Start Date: | 2005-04-10 | [6 empty] | Alternate Gantt Start Date:
| PROJECT NAME: | <Project Name> | [9 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 32 | 33 | 36 | 37 | 38 | 39 | 40 | 43 | 44 | 45 | 46 | 47 | 50 | 51 | 52 | 53 | 54 | 57 | 58 | 59 | 60 | 61 | 64 | 65 | 66 | 67 | 68 | 71 | 72 | 73 | 74 | 75 | 78 | 79 | 80 | 81 | 82 | 85 | 86 | 87 | 88 | 89 | 92 | 93 | 94 | 95 | 96 | 99 | 100 | 101 | 102 | 103 | 106 | 107 | 108 | 109 | 110 | 113 | 114 | 115 | 116 | 117 | 120 | 121 | 122 | 123 | 124 | 127 | 128 | 129 | 130 | 131 | 134 | 135 | 136 | 137 | 138 | 141 | 142 | 143 | 144 | 145 | 148 | 149 | 150 | 151 | 152 | 155 | 156 | 157 | 158 | 159 | 162 | 163 | 164 | 165 | 166 | 169 | 170 | 171 | 172 | 173 | 176 | 177 | 178 | 179 | 180 | 183 | 184 | 185 | 186 | 187 | 190 | 191 | 192 | 193 | 194 | 197 | 198 | 199 | 200 | 201 | 204 | 205 | 206 | 207 | 208 | 211 | 212 | 213 | 214 | 215 | 218 | 219 | 220 | 221 | 222 | 225 | 226 | 227 | 228 | 229 | 232 | 233 | 234 | 235 | 236 | 239 | 240 | 241 | 242 | 243 | 246 | 247 | 248 | 249 | 250 | 253 | 254 | 255 | 256 | 257 | 260 | 261 | 262 | 263 | 264 | 267 | 268 | 269 | 270 | 271 | 274 | 275 | 276 | 277 | 278 | 281 | 282 | 283 | 284 | 285 | 288 | 289 | 290 | 291 | 292 | 295 | 296 | 297 | 298 | 299 | 302 | 303 | 304 | 305 | 306 | 309 | 310 | 311 | 312 | 313 | 316 | 317 | 318 | 319 | 320 | 323 | 324 | 325 | 326 | 327 | 330 | 331 | 332 | 333 | 334
| PROJECT MANAGER: | <Project Manager> | [8 empty] | Year | 1: #VALUE!; 15: #VALUE!; 29: #VALUE!; 43: #VALUE!; 57: #VALUE!; 71: #VALUE!; 85: #VALUE!; 99: #VALUE!; 113: #VALUE!; 127: #VALUE!; 141: #VALUE!; 155: #VALUE!; 169: #VALUE!; 183: #VALUE!; 197: #VALUE!; 211: #VALUE!; 225: #VALUE!; 239: #VALUE!; 253: #VALUE!; 267: #VALUE!; 281: #VALUE!; 295: #VALUE!; 309: #VALUE!; 323: #VALUE!
[11 empty] | Month | 1: 2005-04-04; 8: 2005-04-11; 15: 2005-04-18; 22: 2005-04-25; 29: 2005-05-02; 36: 2005-05-09; 43: 2005-05-16; 50: 2005-05-23; 57: 2005-05-30; 64: 2005-06-06; 71: 2005-06-13; 78: 2005-06-20; 85: 2005-06-27; 92: 2005-07-04; 99: 2005-07-11; 106: 2005-07-18; 113: 2005-07-25; 120: 2005-08-01; 127: 2005-08-08; 134: 2005-08-15; 141: 2005-08-22; 148: 2005-08-29; 155: 2005-09-05; 162: 2005-09-12; 169: 2005-09-19; 176: 2005-09-26; 183: 2005-10-03; 190: 2005-10-10; 197: 2005-10-17; 204: 2005-10-24; 211: 2005-10-31; 218: 2005-11-07; 225: 2005-11-14; 232: 2005-11-21; 239: 2005-11-28; 246: 2005-12-05; 253: 2005-12-12; 260: 2005-12-19; 267: 2005-12-26; 274: 2006-01-02; 281: 2006-01-09; 288: 2006-01-16; 295: 2006-01-23; 302: 2006-01-30; 309: 2006-02-06; 316: 2006-02-13; 323: 2006-02-20; 330: 2006-02-27
WBS | TASKS | RESOURCE | PLANNED START DATE | PLANNED FINISH DATE | STATUS | Comp % | ACTUAL FINISH DATE | NOTES |  |  | Week # | 1: #VALUE!; 8: #VALUE!; 15: #VALUE!; 22: #VALUE!; 29: #VALUE!; 36: #VALUE!; 43: #VALUE!; 50: #VALUE!; 57: #VALUE!; 64: #VALUE!; 71: #VALUE!; 78: #VALUE!; 85: #VALUE!; 92: #VALUE!; 99: #VALUE!; 106: #VALUE!; 113: #VALUE!; 120: #VALUE!; 127: #VALUE!; 134: #VALUE!; 141: #VALUE!; 148: #VALUE!; 155: #VALUE!; 162: #VALUE!; 169: #VALUE!; 176: #VALUE!; 183: #VALUE!; 190: #VALUE!; 197: #VALUE!; 204: #VALUE!; 211: #VALUE!; 218: #VALUE!; 225: #VALUE!; 232: #VALUE!; 239: #VALUE!; 246: #VALUE!; 253: #VALUE!; 260: #VALUE!; 267: #VALUE!; 274: #VALUE!; 281: #VALUE!; 288: #VALUE!; 295: #VALUE!; 302: #VALUE!; 309: #VALUE!; 316: #VALUE!; 323: #VALUE!; 330: #VALUE!
[9 empty] | Cal Start | Cal End | Work Days | 1: 2005-04-04; 8: 2005-04-11; 15: 2005-04-18; 22: 2005-04-25; 29: 2005-05-02; 36: 2005-05-09; 43: 2005-05-16; 50: 2005-05-23; 57: 2005-05-30; 64: 2005-06-06; 71: 2005-06-13; 78: 2005-06-20; 85: 2005-06-27; 92: 2005-07-04; 99: 2005-07-11; 106: 2005-07-18; 113: 2005-07-25; 120: 2005-08-01; 127: 2005-08-08; 134: 2005-08-15; 141: 2005-08-22; 148: 2005-08-29; 155: 2005-09-05; 162: 2005-09-12; 169: 2005-09-19; 176: 2005-09-26; 183: 2005-10-03; 190: 2005-10-10; 197: 2005-10-17; 204: 2005-10-24; 211: 2005-10-31; 218: 2005-11-07; 225: 2005-11-14; 232: 2005-11-21; 239: 2005-11-28; 246: 2005-12-05; 253: 2005-12-12; 260: 2005-12-19; 267: 2005-12-26; 274: 2006-01-02; 281: 2006-01-09; 288: 2006-01-16; 295: 2006-01-23; 302: 2006-01-30; 309: 2006-02-06; 316: 2006-02-13; 323: 2006-02-20; 330: 2006-02-27
1 | WBS Element 1 |  | 2005-04-10 | 2005-05-19 |  |  |  |  | 7 | 46 | 29 | bar: 8 to 46
1.1 | Propose project | Name | 2005-04-10 | 2005-04-12 | Completed | 100% | 2005-04-12 |  | 7 | 9 | 2 | 8: 3; 9: 3
1.2 | Committee consideration/approval | Name | 2005-04-12 | 2005-04-20 | Completed | 100% | 2005-04-20 |  | 9 | 17 | 7 | 9: 3; 10: 3; 11: 3; 12: 3; 15: 3; 16: 3; 17: 3
1.3 | Material Preparation | Name | 2005-04-20 | 2005-05-08 | In Progress | 80% |  |  | 17 | 35 | 13 | 17: 2; 18: 2; 19: 2; 22: 2; 23: 2; 24: 2; 25: 2; 26: 2; 29: 2; 30: 2; 31: 2; 32: 2; 33: 2
1.4 | Prepare Invitations & Flyers | Name | 2005-04-25 | 2005-04-28 | In Progress | 40% |  |  | 22 | 25 | 4 | 22: 2; 23: 2; 24: 2; 25: 2
1.5 | Send/post invitations & flyers | Name | 2005-04-29 | 2005-04-29 |  |  |  |  | 26 | 26 | 1 | bar: 26
1.6 | Arrange/prepare room | Name | 2005-05-09 | 2005-05-10 |  |  |  |  | 36 | 37 | 2 | bar: 36 to 37
1.7 | Rehearse/edit materials | Name | 2005-05-11 | 2005-05-16 |  |  |  |  | 38 | 43 | 4 | bar: 38 to 43
1.8 | PRESENTATIONS | Name | 2005-05-17 | 2005-05-19 |  |  |  |  | 44 | 46 | 3 | bar: 44 to 46
1.9 | Task I | Name | [8 empty] | 0
1.1 | Task J | Name | [8 empty] | 0
2 | WBS Element 2 | [7 empty] | 0 | 0 | 0
2.1 | Task A | Name | [8 empty] | 0
2.2 | Task B | Name | [8 empty] | 0
2.3 | Task C | Name | [8 empty] | 0
2.4 | Task D | Name | [8 empty] | 0
2.5 | Task E | Name | [8 empty] | 0
2.6 | Task F | Name | [8 empty] | 0
2.7 | Task G | Name | [8 empty] | 0
2.8 | Task H | Name | [8 empty] | 0
2.9 | Task I | Name | [8 empty] | 0
2.1 | Task J | Name | [8 empty] | 0
3 | WBS Element 3 | [7 empty] | 0 | 0 | 0
3.1 | Task A | Name | [8 empty] | 0
3.2 | Task B | Name | [8 empty] | 0
3.3 | Task C | Name | [8 empty] | 0
3.4 | Task D | Name | [8 empty] | 0
3.5 | Task E | Name | [8 empty] | 0
3.6 | Task F | Name | [8 empty] | 0
3.7 | Task G | Name | [8 empty] | 0
3.8 | Task H | Name | [8 empty] | 0
3.9 | Task I | Name | [8 empty] | 0
3.1 | Task J | Name | [8 empty] | 0
4 | WBS Element 4 | [7 empty] | 0 | 0 | 0
4.1 | Task A | Name | [8 empty] | 0
4.2 | Task B | Name | [8 empty] | 0
4.3 | Task C | Name | [8 empty] | 0
4.4 | Task D | Name | [8 empty] | 0
4.5 | Task E | Name | [8 empty] | 0
4.6 | Task F | Name | [8 empty] | 0
4.7 | Task G | Name | [8 empty] | 0
4.8 | Task H | Name | [8 empty] | 0
4.9 | Task I | Name | [8 empty] | 0
4.1 | Task J | Name | [8 empty] | 0
5 | WBS Element 5 | [7 empty] | 0 | 0 | 0
5.1 | Task A | Name | [8 empty] | 0
5.2 | Task B | Name | [8 empty] | 0
5.3 | Task C | Name | [8 empty] | 0
5.4 | Task D | Name | [8 empty] | 0
5.5 | Task E | Name | [8 empty] | 0
5.6 | Task F | Name | [8 empty] | 0
5.7 | Task G | Name | [8 empty] | 0
5.8 | Task H | Name | [8 empty] | 0
5.9 | Task I | Name | [8 empty] | 0
5.1 | Task J | Name | [8 empty] | 0
6 | WBS Element 6 | [7 empty] | 0 | 0 | 0
6.1 | Task A | Name | [8 empty] | 0
6.2 | Task B | Name | [8 empty] | 0
6.3 | Task C | Name | [8 empty] | 0
6.4 | Task D | Name | [8 empty] | 0
6.5 | Task E | Name | [8 empty] | 0
6.6 | Task F | Name | [8 empty] | 0
6.7 | Task G | Name | [8 empty] | 0
6.8 | Task H | Name | [8 empty] | 0
6.9 | Task I | Name | [8 empty] | 0
6.1 | Task J | Name | [8 empty] | 0
Note on F1: This is the earliest date from either the dates below or the alternative date to the right.
Note on M6: Assumes 5 work days per calendar week
Note on N1: Any entered date becomes first date displayed in Gantt below. Leave blank to use earliest task start date as Gantt start.
Note on N6: The first date is converted to be a Monday since that may not be the case from pre-entered dates.