## Gatt graph-001
Project implementation schedule
| Project start time： | 2009-05-26 |  | reporter:
number | mission name | Planned working hours | Starting time | Planned completion time | Actual completion date | Actual working hours | 图表数据 | Early completion time | Lag time
1 | Equipment arrival receipt | 1 | 2009-05-26 | 2009-05-26 | 2009-05-26 | 1 | 1 | 0 | 0
2 | Equipment arrival acceptance | 1 | 2009-06-01 | 2009-06-01 | 2009-06-17 | 17 | 1 |  | 16
3 | Equipment rack | 2 | 2009-06-02 | 2009-06-03 | 2009-06-03 | 2 | 2 | 0 | 0
4 | Server installation（Win or HP-UX) | 3 | 2009-06-04 | 2009-06-06 | 2009-06-06 | 3 | 3 | 0 | 0
5 | Host room storage configuration and debugging | 2 | 2009-06-04 | 2009-06-05 | 2009-06-05 | 2 | 2 | 0 | 0
6 | Main and auxiliary equipment room cable construction | 6 | 2009-06-06 | 2009-06-14 | 2009-06-14 | 6 | 6 | 0 | 0
7 | Backup machine room configuration and debugging | 1 | 2009-06-15 | 2009-06-15 | 2009-06-15 | 1 | 1 | 0 | 0
8 | VCS cluster installation configuration（For Win or Hp-ux) | 2 | 2009-06-15 | 2009-06-16 | 2009-06-15 | 1 | 1 | 1
9 | Sybase Database installation | 2 | 2009-06-17 | 2009-06-18 | 2009-06-18 | 2 | 2 | 0 | 0
10 | Sqlserver Database installation | 2 | 2009-06-17 | 2009-06-18 | 2009-06-19 | 3 | 2 |  | 1
11 | Sybase migration test | 4 | 2009-06-19 | 2009-06-24 |  |  | 4
12 | Sybase migration test | 4 | 2009-06-19 | 2009-06-24 | 2009-06-25 | 5 | 4 |  | 1
13 | Sybase Database migration | 2 | 2009-06-25 | 2009-06-26
14 | Sqlserver Database migration | 2 | 2009-06-25 | 2009-06-26 |  |  | 2
15 | Computer room migration | 2 | 2009-06-26 | 2009-06-27 |  |  | 2
16 | Veritas mirror software installation and configuration | 3 | 2009-06-29 | 2009-07-01
17 | Veritas NBU backup software installation and configuration | 3 | 2009-06-29 | 2009-07-01 |  |  | 3
18 | Network implementation | 8 | 2009-06-08 | 2009-06-17 |  |  | 8
19 | Project Acceptance | 4 | 2009-07-01 | 2009-07-04
legend: |  |  | planning schedule |  |  | Completed ahead of schedule |  |  |  | extension
Formulas:
Planned completion time = IF(OR([Planned working hours]="",[Starting time]=""),"",(([Starting time]+[Planned working hours])-1))
Planned completion time = IF(OR([Planned working hours]="",[Starting time]=""),"",(([Starting time]+[Planned working hours])+2))