## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
2017
2018
Today
Aug
Sep
Oct
Nov
Dec
2018
Feb
Mar
Secure Budget
08.19
Identify PM
10.22
Set-up Certification
12.15
Production Begins
02.08
Analyze Results
03.04
Determine Objectives
08.02
Select Vendor
09.27
Stakeholder Review
11.30
System Check
12.29
Wrap-up Audit
02.28
Project Sourcing
08.20 - 09.23
5 wks
Project Readiness
10.02 - 12.03
9 wks
Development Phase
10.15 - 02.03
16 wks
Testing and Reviews
01.03 - 02.06
5 wks
Documentation
01.01 - 02.04
5 wks
Adjustment Phase
02.08 - 02.28
3 wks